## week 2
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1792395 |  |  | Week starting: | 2
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-08 | 20:00 | 22:00 | 4 | Learning React Native | We decided to use React Native as devloping language | Enrolled and started in a online course in edX about mobile app development in React Native
Tuesday | 2021-03-09 | 17:00 | 18:00 | 1 | Group internal meeting in person | Discuss the interface and resources | We discussed about the major functionality and interface layout and decided to use Figma for interface design; shared online resources of learning React Native; I found out that I have not been added to the GitHub team repository so I decided to send an email to lecturer about it
Tuesday | 2021-03-09 | 20:00 | 22:00 | 4 | Learning React Native | We decided to use React Native as devloping language | Enrolled and started in a online course in edX about mobile app development in React Native
Wednesday | 2021-03-10 | 20:00 | 22:00 | 2 | Making demo interface elements in Photoshop | To statisfiy our clients' preference on using bubble chart to illustrate the emotions in the interface | 5 emomtions bubble with transaprenet in png format
Thursday | 2021-03-11 | 16:00 | 17:00 | 1 | Group internal meeting in Zoom | Prepare for week 3 client meeting and pitch presentation | Discuss the meeting agenda, interface orototype v0.5 and amended changes, set internal deadlines of pitch presentation slide to 19 March
|  | 20:00 | 22:00 | 2 | Learn the Ionic Framework with Angular for mobile app development | Our clients require us to use Ionic instead of React Native to develop the App | Started to watch Ionic tutorial video on Youtube
Friday | 2021-03-12 | 20:00 | 22:00 | 2 | Research on existing App in market | We need to compare our product to existing App in market to find out why is our product better than others | Adopted design some ideas from existing App, but also found out the differences between our product and existing solution
Saturday | 2021-03-13 | 15:00 | 19:00 | 4 | Learn the Ionic Framework with Angular for mobile app development | Learn the framwork and language for developing our App | Continue to watch Ionic tutorial video on Youtube
|  |  | Total | 20

## week 3
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1792395 |  |  | Week starting: | 3
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-15 | 19:00 | 23:00 | 4 | Learn the Ionic Framework with Angular for mobile app development | Learn the framwork and language for developing our App | Continue to watch Ionic tutorial video on Youtube
Tuesday | 2021-03-16 | 14:00 | 14:30 | 0.5 | Meeting with client in Zoom | Discuss the protype design and prioritise major features | To change the prototype design as per clients request, including the layout of explore page and home page
Tuesday | 2021-03-16 | 14:30 | 15:30 | 1 | Group internal meeting in Zoom | weekly planing for the project | prepare for pitch presentation, discussed and adjust the prototype to satisfied clients' requirements
Wednesday | 2021-03-17 | 20:00 | 22:00 | 2 | Adjust the pitch slide | prepare for pitch presentation | Changed the content of pitch slide as per internal group discussion
Thursday | 2021-03-18 | 19:00 | 23:00 | 4 | Learn the Ionic Framework with Angular for mobile app development | Learn the framwork and language for developing our App | Continue to watch Ionic tutorial video on Youtube
Friday | 2021-03-19 | 16:00 | 17:00 | 1 | Group internal meeting in Zoom | Prepare for week 4 client meeting and pitch presentation | Prepare for week 4 agenda, adjust pitch slide
Saturday | 2021-03-20 | 19:00 | 23:00 | 4 | Learn the Ionic Framework with Angular for mobile app development | Learn the framwork and language for developing our App | Continue to watch Ionic tutorial video on Youtube
Sunday | 2021-03-21 | 19:00 | 23:00 | 4 | Learn the Ionic Framework with Angular for mobile app development | Learn the framwork and language for developing our App | Continue to watch Ionic tutorial video on Youtube
|  |  | Total | 20.5

## week 4
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1792395 |  |  | Week starting: | 4
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-22 | 19:00 | 23:00 | 4 | Learn the Ionic Framework with Angular for mobile app development | Learn the framwork and language for developing our App | Continue to watch Ionic tutorial video on Youtube
Tuesday | 2021-03-23 | 14:00 | 14:30 | 0.5 | Meeting with client in Zoom | Discuss the protype design and pitch presentation | We adjusted the pitch slide and remove the parts that clients consider as not important
Tuesday | 2021-03-23 | 14:30 | 15:30 | 1 | Group internal meeting in Zoom | weekly planing for the project | prepare for pitch presentation, discussed and adjust the slide to satisfied clients' requirements
Tuesday | 2021-03-23 | 19:00 | 23:00 | 4 | Learn the Ionic Framework with Angular for mobile app development | Learn the framwork and language for developing our App | Continue to watch Ionic tutorial video on Youtube
Wednesday | 2021-03-24 | 21:00 | 22:00 | 2 | Prepare the minutes on week 4 client meeting | A wrap up of clients meeting | summarize the ideas and comments from clients
Thursday | 2021-03-25 | 19:00 | 23:00 | 4 | Learn the Ionic Framework with Angular for mobile app development | Learn the framwork and language for developing our App | Continue to watch Ionic tutorial video on Youtube
Friday | 2021-03-26 | 19:00 | 23:00 | 4 | Modify the pitch slide | prepare for pitch presentation | Modify the feasibility part, mostly focus on milestone, cooperation with client's lab, and techlonogy stack
Saturday | 2021-03-27 | 14:45 | 16:00 | 1.25 | Group internal meeting in Zoom | Prepare for week 5 client meeting, business case, milestone and pitch presentation | Prepare for week 5 agenda, work on business case and milestone
|  |  | Total | 20.75

## week 5
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1792395 |  |  | Week starting: | 5
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-29 | 18:00 | 21:00 | 4 | Writing draft of speech and recording the pitch video | Part of pitch presentation | Written form of pitch drafted and video recorded
Monday | 2021-03-29 | 21:00 | 23:30 | 4 | Combining all team member's pitch video | Prepare for the upload of pitch presentation | All team member's video combined with balanced volume
Tuesday | 2021-03-30 | 15:00 | 18:00 | 3 | Group internal meeting in Uni | Sharing learning outcome on Ionic and Angular, budiling App as draft | Built landing page, draft of home page, and empty pages for others
Wednesday | 2021-03-31 | 18:00 | 22:00 | 4 | Learn the Ionic Framework with Angular for mobile app development | Learn the framwork and language for developing our App | Continue to watch Ionic tutorial video on Youtube
Thursday | 2021-04-01 | 15:00 | 16:00 | 1 | Group internal meeting | Write business case and milesteon 1 plan | Amended the business case and milestone 1 plan
Saturday | 2021-04-03 | 20:00 | 22:00 | 2 | Learn the Ionic Framework with Angular for mobile app development | Learn the framwork and language for developing our App | Continue to watch Ionic tutorial video on Youtube
Sunday | 2021-04-04 | 20:00 | 22:30 | 4 | Finalized and upload business case and milestone plan | Finalized, proofread, formatted and page adjusted the business case and milestone plan | Finalized business case and draft output as PDF file and submitted
|  |  | Total | 22

## week 6
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1792395 |  |  | Week starting: | 6
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-04-05 | 19:00 | 23:00 | 4 | Learn the Ionic Framework with Angular for mobile app development | Learn the framwork and language for developing our App | Continue to watch Ionic tutorial video on Youtube
Tuesday | 2021-04-07 | 15:00 | 18:00 | 3 | Team Meeting in campus | Staring milestone 1 development | Worked on milestone demo
Wednesday | 2021-04-08 | 19:00 | 23:00 | 4 | Learn the Ionic Framework with Angular for mobile app development | Learn the framwork and language for developing our App | Continue to watch Ionic tutorial video on Youtube
Thursday | 2021-04-09 | 19:00 | 23:00 | 3 | Learn the CSS | Learn the CSS language for developing our App | read CSS tutorial on website
Friday | 2021-04-10 | 16:00 | 17:00 | 1 | Team Meeting | Help plan, organise and track project development process | Adjust project scope according to clients' requirements
Friday | 2021-04-10 | 18:00 | 23:00 | 5 | Developing demo as milestone 1 planned | Staring milestone 1 development | Worked on milestone demo
Sunday | 2021-04-12 | 20:00 | 22:30 | 4 | working on Home page | Milestone 1 development | admended the CSS
|  |  | Total | 24

## MidBreak
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1792395 |  |  | Week starting: | MidBreak
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Thursday | 2021-04-15 | 19:00 | 23:00 | 4 | Learn the Ionic Framework with Angular for mobile app development | Learn the framwork and language for developing our App | Continue to watch Ionic tutorial video on Youtube
Saturday | 2021-04-17 | 14:00 | 17:00 | 3 | Team Meeting in campus | Discuss team member's developing progress | Learn Django and Firebase
Sunday | 2021-04-18 | 19:00 | 23:00 | 3 | Learn the CSS | Learn the CSS language for developing our App | read CSS tutorial on website
Monday | 2021-04-19 | 15:00 | 18:00 | 3 | Developing demo as milestone 1 planned | Staring milestone 1 development | Worked on home page
Wednesday | 2021-04-21 | 19:00 | 23:00 | 4 | Learn the Ionic Framework with Angular for mobile app development | Learn the framwork and language for developing our App | Continue to watch Ionic tutorial video on Youtube
Thursday | 2021-04-22 | 14:00 | 17:00 | 3 | Team Meeting in campus | Prepare for milestone 1 report and discuss team member's developing progress
Thursday | 2021-04-22 | 21:00 | 23:00 | 2 | Designing graphic elements for the app | Elements used for developing the Home page | Designed bulbbles image for home page
Friday | 2021-04-23 | 19:00 | 23:00 | 4 | Writing the milestone 1 report | Prepare for milestone 1 report after discuss team member's developing progress | Drafted achieved output and reflection
|  |  | Total | 26

## week 7
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1792395 |  |  | Week starting: | 7
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-04-26 | 13:00 | 16:00 | 3 | Learn the CSS | Learn the CSS language for developing our App | read CSS tutorial on website
Tuesday | 2021-04-27 | 15:00 | 18:00 | 2.5 | Client Meeting + Team Meeting | Prepare for milestone 1 report | Present our progress and work on milestone 1 report after client's meeting
Wednesday | 2021-04-28 | 14:00 | 18:00 | 4 | Learn the Ionic Framework with Angular for mobile app development | Learn the framwork and language for developing our App | Continue to watch Ionic tutorial video on Youtube
Thursday | 2021-04-29 | 19:00 | 23:00 | 4 | working on strageies page | App development | work on front end of strageies page
Friday | 2021-04-30 | 16:00 | 17:00 | 2 | Learn the Ionic Framework with Angular for mobile app development | Learn the framwork and language for developing our App | Continue to watch Ionic tutorial video on Youtube
Saturday | 2021-05-01 | 14:00 | 16:00 | 2 | Team Meeting | Plan, organise and track project development process | Adjust our plan base on clients' comments
Sunday | 2021-05-02 | 19:00 | 23:00 | 4 | working on strageies page | App development | work on front end of strageies page
|  |  | Total | 21.5

## week 8
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1792395 |  |  | Week starting: | 8
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-03 | 15:00 | 18:00 | 3 | Learn the CSS | Learn the CSS language for developing our App | read CSS tutorial on website
Tuesday | 2021-05-04 | 19:00 | 23:00 | 4 | working on explore page | App development | start to work on front end of explore page
Wednesday | 2021-05-05 | 19:00 | 23:00 | 4 | Learn the Ionic Framework with Angular for mobile app development | Learn the framwork and language for developing our App | Continue to watch Ionic tutorial video on Youtube
Thursday | 2021-05-06 | 19:00 | 23:00 | 4 | working on strageies page | App development | work on front end of explore page
Friday | 2021-05-07 | 11:30 | 14:00 | 3 | Client Meeting + Team Meeting | Present the development progress of milestone 1 | Present our progress and work on milestone2 in team meeting
Saturday | 2021-05-08 | 14:00 | 16:00 | 2 | Final Milestone plan | Prepare for second milestone | Drafting the final milestone plan
Sunday | 2021-05-09 | 19:00 | 23:00 | 4 | working on explore page | App development | start to work on front end of explore page
|  |  | Total | 24

## week 9
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1792395 |  |  | Week starting: | 8
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-10 | 18:00 | 21:00 | 3 | working on explore page | App development | work on front end of explore page
Tuesday | 2021-05-11 | 19:00 | 23:00 | 4 | Drafting testing plan | Drafting testing plan | Drafting introduction and unit testing
Wednesday | 2021-05-12 | 18:00 | 21:00 | 3 | Learn the Ionic Framework with Angular for mobile app development | Learn the framwork and language for developing our App | Continue to watch Ionic tutorial video on Youtube
Thursday | 2021-05-13 | 18:00 | 21:00 | 3 | working on explore page | App development | work on front end of explore page
Friday | 2021-05-14 | 19:00 | 23:00 | 4 | Drafting testing plan | Drafting testing plan | Continue to write unit testing
Saturday | 2021-05-15 | 15:00 | 17:00 | 2 | Final Milestone plan | Prepare for next client meeting and discuss the testing plan | Drafting the testing plan
Sunday | 2021-05-16 | 19:00 | 23:00 | 4 | Drafting testing plan | Drafting testing plan | Drafting test schedule and appendix I
|  |  | Total | 23

## week 10
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1792395 |  |  | Week starting: | 8
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-17 | 19:00 | 21:00 | 2 | working on explore page | App development | work on front end of explore page
Tuesday | 2021-05-18 | 19:00 | 23:00 | 4 | working on explore page | App development | work on front end of explore page
Wednesday | 2021-05-19 | 19:00 | 23:00 | 4 | working on explore page | App development | work on front end of explore page
Thursday | 2021-05-20 | 18:00 | 21:00 | 3 | working on explore page | App development | work on front end of explore page
Friday | 2021-05-21 | 19:00 | 21:00 | 2 | Team Meeting | Present our progress in the final milestone | reported our process in each person's part and continue fix defects found in the meeting
Saturday | 2021-05-22 | 15:00 | 18:00 | 3 | working on explore and strategies page | App development | fix the defects found in team meeting
Sunday | 2021-05-23 | 19:00 | 23:00 | 4 | working on explore and strategies page | App development | fix the defects found in team meeting
|  |  | Total | 22

## week 11
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1792395 |  |  | Week starting: | 8
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-24 | 19:00 | 23:00 | 4 | Modifying the UI design of Explore page | App development | Modifying the UI design of Explore page
Tuesday | 2021-05-25 | 16:00 | 18:00 | 2 | Client meeting | Demo of final mileston | We received feedback from clients
Wednesday | 2021-05-26 | 18:00 | 21:00 | 3 | working on explore page | App development | modifying the explore page accordin to clients comments
Thursday | 2021-05-27 | 19:00 | 23:00 | 4 | working on straegies page | App development | modifying the straegies page accordin to clients comments
Friday | 2021-05-28 | 18:00 | 21:00 | 3 | Drafting poster | Poster | Drafting poster
Saturday | 2021-05-29 | 16:00 | 18:00 | 2 | Group meeting | Poster | Discuss the progress of poster draft and give feedback to each other
Sunday | 2021-05-30 | 19:00 | 23:00 | 4 | Drafting poster | Poster | Drafting poster
|  |  | Total | 22

## week 12
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1792395 |  |  | Week starting: | 8
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-31 | 19:00 | 21:00 | 2 | Drafting poster | Poster | Drafting poster
Tuesday | 2021-06-01 | 18:00 | 21:00 | 3 | Drafting poster | Poster | Drafting poster
Wednesday | 2021-06-02 | 19:00 | 23:00 | 4 | Drafting Final report | Final report | Drafting Final report
Thursday | 2021-06-03 | 19:00 | 21:00 | 2 | Drafting Final report | Final report | Drafting Final report
Friday | 2021-06-04 | 15:00 | 18:00 | 3 | Go to Zoom session for poster feedback | Poster | Presented the poster draft to Cruz and collected the comments to team member for reference
Saturday | 2021-06-05 | 15:00 | 18:00 | 3 | Modifying poster | Poster | Modifying poster according to Cruz's feedback
Sunday | 2021-06-06 | 18:00 | 23:30 | 5.5 | Modifying poster, recording for the poster, poster video editing | Poster | Modifying poster according to Cruz's feedback, final formatting the poster, recording for the poster, and combining team member's part of recording to the poster vidro
|  |  | Total | 22.5